Project reference No: 16-A-021

PROJECT REPORT

Project name:   Tilapia and Cat-fish production micro-enterprise for 150 people at Ndevelwa village.

Organization name:  Archdiocese of Tabora, Caritas Tabora.

Date Funds Received:  9/5/2016

Project implementer:   Rev.Fr. Alex Nduwayo

1: Project outcomes – the results achieved.

The project has brought a great benefit to the target group and Ndevelwa community at large since they have acquired modern fish production knowledge. Having adapted fish production techniques, some people have started to practice fish production at their home place where they establish small fish ponds in which they produce fish for family use and economic purpose.  Having fish ponds at Ndevelwa, now the community is using fish for food, which in a long term will assist the decrease of malnutrition problem to Ndevelwa community. Apart from that, production of fish at Ndevelwa has paved the way to earning money because as time goes they sell fish and earn income for their betterment.

2: Financial accountability- how the money was spent

| Item | Electric Aid | Local contribution | Total Tsh. |
| --- | --- | --- | --- |
| Training activities |  |  |  |
| Photocopy paper (reams)5 |  | 75,000 | 75,000 |
| Files |  | 25,000 | 25,000 |
| Office pins |  | 10,000 | 10,000 |
| Box files |  | 90,000 | 90,000 |
| Staple pins |  | 8,000 | 8,000 |
| Stapler machines |  | 20,000 | 20,000 |
| Punching mach. |  | 20,000 | 20,000 |
| Carbon paper |  | 50,000 | 50,000 |
| Ball pen |  | 20,000 | 20,000 |
| Note books |  | 40,000 | 40,000 |
| Dairy () |  | 8,000 | 8,000 |
| Fluid glue* ( Bottle) |  | 5,000 | 5,000 |
| Cell tape |  | 10,000 | 10,000 |
| Stamp pad* |  | 6,000 | 6,000 |
| Stamp ink |  | 20,000 | 20,000 |
| Cartilage |  | 2,200,000 | 2,200,000 |
| Envelope-small size(250) |  | 30,000 | 30,000 |
|  |  | 2,637,000 | 2,637,000 |
| Rehabiltation of 3 ponds. |  |  |  |
| Timbers-soft wood 2*4” 80 | 645,000 |  | 645,000 |
| Timbers2”*3”(50pcs)* | 255,000 |  | 255,000 |
| Mild steel iron 14mm | 300,000 |  | 300,000 |
| Ceiling board sheets(70)* 70 | 905,000 |  | 905,000 |
| Paint 20tins | 940,000 |  | 940,000 |
| Cement | 800,000 |  | 800,000 |
| Sand | 500,000 |  | 500,000 |
| Gravel | 240,000 |  | 240,000 |
| Construction expenses | 180,000 |  | 180,000 |
| Dyke renovation* | 2,000,000 |  | 2,000,000 |
| In /outlet renovation | 1,950,000 |  | 1,950,000 |
| Fencing* | 1,869,000 |  | 1,869,000 |
|  | 10,584,000 |  | 10,584,000 |
| Other Materials |  |  |  |
| Aerators (air pumps) | 300,500 |  | 300,500 |
| ph metre | 50,200 |  | 50,200 |
| Heater | 13,500 |  | 13,500 |
| Basin(large size) | 40,400 |  | 40,400 |
| Basin(small size) | 24,000 |  | 24,000 |
| Trays* | 20,000 |  | 20,000 |
| Net sheet | 3,000 |  | 3,000 |
| Syringe & needle | 2,000 |  | 2,000 |
| Bowls | 2,000 |  | 2,000 |
| Scissors(stainless)* | 10,700 |  | 10,700 |
| Towels | 30,000 |  | 30,000 |
| 1Eletrical w/scale* | 470,000 |  | 470,000 |
| Electrical bulb | 2,000 |  | 2,000 |
| Nylon ropes | 1,800 |  | 1,800 |
| Manure (1 tone) | 450,500 |  | 450,500 |
| Lime(KGS) | 2,171,000 |  | 2,550,000 |
| TSP(BAGS) | 1,400,000 |  | 1,400,000 |
| Fish feeds (bags) | 508,500 |  | 508,500 |
| Cat fish broods(100)* | 600,000 |  | 600,000 |
| Tilapia fingerlings (540x6)* | 60,000 |  | 60,000 |
| HCG(2doz.) | 398,000 |  | 398,000 |
| Car services* | 455,000 |  | 455,000 |
| 1 steel cabinet* | 779,400 |  | 779,600 |
|  | 7,792,500 |  | 8,171,700 |
| Operation and Maintenance | 1,000,000 |  | 1,000,000 |
|  | 19,376,500 | 2,637,000 | 22,013,500 |

Fund received in local currency Tsh 19, 800, 000

Actual expenditure Tsh 22,013,500

3: Project Process Narrative- how the project was implemented or progressed to date.

After receiving the fund the target group of 150 people were selected and soon after the selection trainings on modern fish production begun. The training was followed by a practical act where by pond builders worked hand to hand with the target group from the point of building to the point of inserting tilapia and cat-fish seeds. Monitoring the progress of those fish ponds has been the everyday activity done by the target since the seeds were inserted.

Now fish ponds are at good position and they have fish (the production is good) that Ndevelwa community can access fish for food but the target group is searching for markets where they will be selling fish at the reasonable cost.

4: Visual Report- photographs.

Kindly find the photos for more elaboration about the progress of the project in an attachment.

5: Our comments

Ndevelwa village are seeing themselves as a lucky community for this wonderful project, this is because apart from having fish as food ,source of income and the learning center, they have also acquired a knowledge of fish production which will benefit even the coming  generation. Through Caritas they express their great thanks to Electric Aid for your concern to support and ask to be with them always so as to change the living standard of Ndevelwa citizens.

The community has promised to make sure that the fish ponds are well kept that the production benefits even the coming generation and be the symbol and remembrance of Electric Aid.