Project reference No: 15-A-189

PROJECT REPORT

Project name:   Poultry micro-enterprise project – Tumbi, Tabora.

Organization name: Archdiocese of Tabora, Caritas Tabora.

Date Funds Received: 18/4/2016

Project implementer: Rev.Fr. Alex Nduwayo

1: Project outcomes- the results achieved.

Poultry micro-enterprise project has brought a great impact to Tumbi community. Down here is an explanation of the project outcomes.

- Foremost the project facilitated establishments of 5 microfinance groups, in such groups, members are saving and accessing loans, up to the reporting period, 80% of the group members have accessed loans for their investments.

- That being the case, it has motivated many people to engage themselves in poultry keeping activities by building poultry cages since seemed easy to manage and it does not need big income.

- Through training, the project has also equipped Tumbi groups with skills on the modern ways of poultry keeping; this has changed the local ideas they had on poultry keeping and increased their production.

VICOBA groups being the target of the project, and taking in mind that in VICOBA is where they access loans to establish poultry investments, the project has helped group members to gain money; repay their loans by selling chickens and get more income from poultry investments. Apart from that, Tumbi residents have leant from VICOBA members; and applied poultry keeping techniques at their households, and as a result, they get both meet and eggs from their chicken. Beyond this, it has been proved that the health of the majority residents of Tumbi village have started to improve their health.

2: Financial accountability- how the money was spend

| Item | Electric Aid | Local contribution | Total Tsh |
| --- | --- | --- | --- |
| Establishment of Microfinance groups |  |  |  |
| Purchase of Microfinance scheme equipments (complete VICOBA materials package) | 600,000 |  | 600,000 |
| Costs for Conduct Capacity building training on Poultry Entrepreneurship |  |  |  |
| Hire Trainer |  | 350,000 | 350,000 |
| Meals for participants |  | 2,400,000 | 2,400,000 |
| Venue |  | 100,000 | 100,000 |
| Transport allowance |  | 1,200,000 | 1,200,000 |
| Stationary |  | 50,000 | 50,000 |
| Costs for Poultry Materials |  |  |  |
| Incubator | 5,000,000 |  | 5,000,000 |
| Installation | 130,000 |  | 130,000 |
| Purchase stock eggs | 100,000 |  | 100,000 |
| Feeds initial stock | 516,000 |  | 516,000 |
| Costs for Construction of chicken Shed |  |  |  |
| Foundation Materials |  |  |  |
| Site Preparation | 200,000 |  | 200,000 |
| Cement | 298,000 |  | 298,000 |
| Aggregates | 258,000 |  | 258,000 |
| Sand | 220,000 |  | 220,000 |
| Hardcore | 280,000 |  | 280,000 |
| Walling Materials |  |  |  |
| Bricks | 1,600,000 |  | 1,600,000 |
| Sand | 310,000 |  | 310,000 |
| Aggregates | 750,000 |  | 750,000 |
| Cement | 460,000 |  | 460,000 |
| Iron Bars 16 MM 1 | 501,200 |  | 501,200 |
| Iron Bars 12 MM | 484,000 |  | 484,000 |
| Binding wire | 139,400 |  | 140,000 |
| Nails Assorted | 112,000 |  | 112,000 |
| Timber 9x1, | 362,000 |  | 362,000 |
| Timber 4x2, | 218,400 |  | 218,400 |
| Roofing Materials |  |  |  |
| Timber 6x2 | 643,000 |  | 643,000 |
| Timber 4x2 | 418,000 |  | 418,000 |
| Timber 3x2 | 205,000 |  | 205,000 |
| Nails Assorted | 240,000 |  | 240,000 |
| Iron sheets | 995,000 |  | 995,000 |
| Nails for roofing | 90,000 |  | 90,000 |
| Oil for treating Timber | 50,000 |  | 50,000 |
| Iron Bars 6mm, | 330,000 |  | 330,000 |
| Iron Ridges | 80,000 |  | 80,000 |
| Binding Wire | 63,000 |  | 63,000 |
| Finishing Materials |  |  |  |
| Sand | 605,000 |  | 605,000 |
| Cement for floor | 650,000 |  | 650,000 |
| Nails | 70,000 |  | 70,000 |
| Windows | 349,000 |  | 349,000 |
| Doors | 308,000 |  | 350,000 |
| Transport of materials |  | 350,000 | 350,000 |
| Labou charge |  | 1,577,600 | 1,577,600 |
| TOTAL | 17,635,000 | 6,027,600 | 23,705,200 |

Fund received Euro 8000 = Tsh 17,600,000

Actual Expenditure Tsh 23,705,200

3: Project Process Narrative- how the project was implemented or progressed to date.

After receiving the fund from Electric Aid, trainings on modern ways to keep poultry begun for 3 Tumbi groups; while the training were going on the civil technician was contacted and the activity of building chicken house (demo house) begun. The house was built with all qualifications of a better poultry house to show the target group that though they will have to use local materials at their places but all recommended qualities should be considered for example  three rooms one for keeping chicken, one for laying and the other for keeping chicks. After the demo house was well built chicks inserted for more training on how to keep poultry in case of vaccination and feeding so that group members and all the community can learn the practice from the demo centre and apply it at their home place.

4: Visual Report- photographs.

Pictorial report is attached for more clarification.

5: Our comments

Caritas Tabora on behalf of Tumbi community they are happy of the project and they express their great thanks to  Electric Aid for supporting and making it possible for Tumbi community to have a place for keeping poultry and learning on different matters concerning poultry such as diseases, vaccination and quality of food to feed chicks.

The project has motivated many people to engage in poultry keeping activities since it is the area they think they can do better due to the training attained. Few months to come poultry keeping will be a highly income generating activity to Tumbi community.